## Q1
Objective | Target | KPI | Main Activity | Sub Activity | Detailed Description | Responsible | Jul | Aug | Sept | IMPLEMENTATION STATUS / REMARKS | Means of verification | OUTCOME | Budget/no budget item
|  |  | To review and improve the underwriting, claim, reinsurance, investment and reporting functionalities of IMIS system by June, 2023 | Conduct System Gap Analysis on General Underwriting | Perform Gap analysis with User on General Individual , Corporate Undewriting and Undewrirting from external stakeholders banc assurance and intermediaries | Imary, Daniel,Kasoma, mohamed, Frank+User Department | √ |  |  |  | Signed Gap Analysis report, user stories matrix | Identified System Defects and area of Improvement
|  |  |  | Redesign the system to address the identified gap | Redesign Individual undewriting process to remove complexity and gaps identified | Imary, Daniel,Kasoma, mohamed, Frank | √ |  |  |  | Design Document including ERD and data Flows
[5 empty] | Redesign Corporate undewriting process to remove complexity and gaps identified and order management | Imary, Daniel,Kasoma, mohamed, Frank | √ |  |  |  | Design Document including ERD and data Flows
|  |  |  | Implement the system (coding) | Coding of Individual underwriting based on the design | imary, Daniel,Kasoma, mohamed, Frank |  | √ | √
[5 empty] | Coding of Corporate Underwriting | Imary, Daniel,Kasoma, mohamed, Frank |  | √ | √
[5 empty] | Report development as per user request | Editha, Halima, Frank |  | √ | √ |  | Signed Report
[5 empty] | Redesgn and optimize Undewriting API, GePG , ERMS Interfaces and Notifications (SMS and Email ) | Imary, Daniel,Machaba,Nyirenda |  |  | √
[5 empty] | Review and redesign Commision Payment | Imary, Daniel |  |  | √ |  | Implementation Report
|  |  |  | System Testing and Migration to Production | Perform UAT on General Undewritings both Individual and Corporate on all Product as well as Commision Payment | ICT +Users |  |  | √ |  | Signed UAT
[5 empty] | Migrate Previous Data to New System, Verify Data Consistance and Accurancy | ICT +Operations +Acturial and Risk |  |  | √ |  | Data Migration and verification Report
[5 empty] | Operationalize General Underwriting Module | ICT Team |  |  | √ |  | Production report and UAT
|  |  |  | Conduct System Gap Analysis of Life Underwriting Process | Perform end to end test with user on life undewriting allocation , commision ,bonus and group life to identify issues/defects | Machaba, Sharifu and Kasoma,Mohamed +User Departments | √ |  |  |  | Signed gap analysis report and other user strories | Identify system defects on individual life undewriting and allocation with area of improvement
|  |  |  | Redesign the system to address the identified gap/issues | Redesign Individual undewriting process , allocation and Commision Payments | Machaba, Sharifu and Kasoma,Mohamed | √ |  |  |  | design Document , ERD and data flow diagram
|  |  |  | Implement the system (coding) | Coding of Individual life underwriting based on the design | Machaba, Sharifu and Kasoma,Mohamed ,effort |  | √ | √
[5 empty] | Allocation redevelopment | Machaba, Sharifu and Kasoma,Mohamed ,effort |  | √ | √
[5 empty] | Coding of Group Underwriting as per Design and scenerio | Machaba, Sharifu and Kasoma,Mohamed ,effort |  | √ | √
[5 empty] | Develop Commision Payments and separate for both Individual and Group | Machaba, Sharifu ,effort |  |  | √
[5 empty] | Report development as per user request | Editha, Halima, Frank |  | √ | √
[5 empty] | Review and redesign Commision Payment and bonus | Machaba,Sharifu, effort |  |  | √
|  |  |  | System Testing and Migration to Production | Perform UAT on Individual, group life, Commision , bonus payment | Machaba, Sharifu and Kasoma,Mohamed ,effort+Users |  |  | √ |  | Signed UAT
[5 empty] | Migrate Previous Data from existing IMIS and CIIS to New System , Verify Data Consistance and Accurancy | Machaba, Sharifu and Kasoma,Mohamed ,effort+Users+risk and Acturial dept |  |  | √ |  | Migration Plan and Data migration Verification report
[5 empty] | Operationalize New System Module | Machaba, Sharifu and Kasoma,Mohamed ,effort+Users |  |  | √
|  |  | To facilitate management of Local Area Connection, Wide Area connection (WAN) and Wireless connection by June, 2023 | Prepare Specification of various item and submit form 2 to procurement | Submit Requisition to purchase 15 network switch | Hamza and Kibiki | √
[5 empty] | Submit requisition to Purchase of Network monitoring Tool (solarwind) | Hamza and Kibiki | √
[5 empty] | Requisition to Purchase of Fire Supression System | Hamza and Kibiki | √
[5 empty] | Purchase of 65" Network Screen Monitoring (Smart TV) | Hamza and Kibiki | √
|  |  | To purchase of Various Working tools 2023 | Prepare Specifications and submit requisition form no 2 | Prepare Specification and submit purchase requisition for 30 Workstation computers | Hamza and Kibiki | √
[5 empty] | Prepare Specification and submit purchase requisition for 27 Laptop Computers for Branch Managers | Hamza and Kibiki | √
[5 empty] | Prepare Specification and submit requisition for 10 Purchase printers | Hamza and Kibiki | √
[5 empty] | Prepare Specificaton Purchase 27 projector | Hamza and Kibiki | √
|  |  | To perform preventive maintance on ICT devices quarterly by June, 2023 | Perform Preventive Maintanace | Prepare TOR to procure contractor and submit requisition for HQ preventive maintanace | Hamza and Kibiki | √
[5 empty] | Prepare Preventive maintanance schedule and perform preventive maintanance per schedule | Hamza and Kibiki | √ |  |  |  | Preventive maitanance schedule
[5 empty] | Perform Preventive maintanance for Printers on HQ and branches | Hamza and Kibiki |  | √ |  |  | Preventive maitanance report
[5 empty] | Perform Preventive maintance of PABX phones | Hamza and Kibiki |  |  | √ |  | work sheet
[5 empty] | Renew NIDC Contract and make Payment | Mohamed/imary |  |  | √
|  |  | To facilitate management of Local Area Connection, Wide Area connection (WAN) and Wireless connection by June, 2023 | Network Monitoring and restructuring | Prepare Plan for Network restructuring | Hamza and Kibiki | √ |  |  |  | Network restructuring Plan
[5 empty] | Restructure the network at HQ data ceter | Hamza and Kibiki |  |  | √ |  | Report
[5 empty] | Upgrade Network devicess at branches per Plan | Hamza and Kibiki |  |  | √ |  | Report
|  |  | Helpdesk Management,health check and Change Request | Resolve all helpdesk queries and change request per KPI | Resolve all helpdesk queries and change request per KPI | ALL | √ | √ | √
|  |  | Report Preparation | Report Preparation | Prepare Quartely ICT status Report (previous quarter report) fro Management and Board | ICTM | √ |  |  |  | Quartly Report
[5 empty] | Perform Risk Assessment | kibiki , mohamed |  |  | √ |  | Risk Register
[5 empty] | Prepare/update ICT Inventory | Hamza and Kibiki |  |  | √ |  | ICT Inventory Report
[5 empty] | Cunduct Monthly Department Meeting for every 1st week of next month | All | √ | √ | √ |  | Meeting minutes
|  |  |  | Cunduct ICT steering Committee meeting | Cunduct ICT steering Committee meeting every first month of the quarter |  | √ |  |  |  | Meeting minutes
Note on J12: User: Will be on the beginning of second qtr , the first wk
Note on J23: User: Actual performanace will on the first week of previous wtr
Note on J39: User: This will overlap to another QTR

## Q2
Objective | Target | KPI | Main Activity | Sub Activity | Detailed Description | Responsible | Oct | Nov | Dec | IMPLEMENTATION STATUS / REMARKS | Means of verification | OUTCOME | Budget/no budget item
|  |  | To review and improve the underwriting, claim, reinsurance, investment and reporting functionalities of IMIS system by June, 2023 | Conduct System Gap Analysis on General Claim Payments | Perform Gap analysis with User on General Claim Process,salvage , reports and integration to ERMS | Imary, Daniel,Kasoma, mohamed, effort,Frank+User Department | √ |  |  |  | Signed Gap Analysis report, user stories matrix | Identified System Defects and area of Improvement
|  |  |  | Redesign the system to address the identified gap | Redesign the process to remove complexity and gaps identified | Imary, Daniel,Kasoma, mohamed, Frank | √ |  |  |  | Design Document including ERD and data Flows
[5 empty] | Redesign interfaces object with accounting system | Imary, Daniel,Kasoma, mohamed, Frank,effort | √ |  |  |  | Design Document including ERD and data Flows
|  |  |  | Implement the system (coding) | Coding of claim process as per new design | imary, Daniel,Kasoma, mohamed, Frank |  | √ | √
[5 empty] | Report development as per user request | Editha, Halima, Frank |  | √ | √ |  | Signed Report
[5 empty] | Coding Claim integration object to ERMS and Notifications (SMS and Email ) | Imary, Daniel,Machaba,effort |  |  | √
|  |  |  | System Testing and Migration to Production | Perform UAT on General General claim Payment | ICT +Users |  |  | √ |  | Signed UAT
[5 empty] | Migrate Previous Data to New System, Verify Data Consistance and Accurancy | ICT +Operations +Acturial and Risk |  |  | √ |  | Data Migration and verification Report
[5 empty] | Operationalize General Claim Module | ICT Team |  |  | √ |  | Filled to Production form and UAT
|  |  |  | Conduct System Gap Analysis of Life Claim payment Process | Perform end to end test with user on individual and group life claim payment , to identify issues/defects | Machaba, Sharifu Mohamed,nyirenda +User Departments | √ |  |  |  | Signed gap analysis report and other user strories | Identify system defects on individual life undewriting and allocation with area of improvement
|  |  |  | Redesign the system to address the identified gap/issues | Redesign Individual and group claim process , allocation and Commision Payments | Machaba, Sharifu ,Mohamed ,nyirenda | √ |  |  |  | design Document , ERD and data flow diagram
|  |  |  | Implement the system (coding) | Coding of Individual life claim payment as per new design | Machaba, Sharifu and ,Mohamed ,effort |  | √ | √
[5 empty] | Coding of Group Claim as per Design and scenerio | Machaba, Sharifu and Kasoma,Mohamed ,effort |  | √ | √
[5 empty] | Report development as per user request | Editha, Halima, Frank |  | √ | √
[5 empty] | Identify data inconsistence issue and causes (CIIS and IMIS) and develop data extraction tool (ETL) | Machaba,Sharifu, effort,mohamed and users |  |  | √
|  |  |  | System Testing and Migration to Production | Perform UAT on Individual, group life,claim payment based on identified user stories and gap identified | Machaba, Sharifu and Mohamed ,nyirenda+Users |  |  | √ |  | Signed UAT
[5 empty] | Migrate Previous Data from existing IMIS and CIIS to New System , Verify Data Consistance and Accurancy | Machaba, Sharifu and Kasoma,Mohamed ,effort+Users+risk and Acturial dept |  |  | √ |  | Migration Plan and Data migration Verification report
[5 empty] | Operationalize New System Module | Machaba, Sharifu and Kasoma,Mohamed ,effort+Users |  |  | √
|  |  | To perform preventive maintance on ICT devices quarterly by June, 2023 | Perform Preventive Maintanace | Perform Preventive maintanance as per schedule | Hamza and Kibiki |  | √ |  |  | Preventive maitanance report
[5 empty] | Perform Preventive maintance of PABX phones | Hamza and Kibiki |  |  | √ |  | work sheet
|  |  | To facilitate management of Local Area Connection, Wide Area connection (WAN) and Wireless connection by June, 2023 | Network Monitoring and restructuring | Monitor Network performance and security | Hamza and Kibiki |  |  | √ |  | Report
[5 empty] | Upgrade Network devicess at branches per Plan | Hamza and Kibiki |  |  | √ |  | Report
|  |  | Helpdesk Management,health check and Change Request | Resolve all helpdesk queries and change request per KPI | Resolve all helpdesk queries and change request per KPI | ALL | √ | √ | √
|  |  | Report Preparation | Report Preparation | Prepare Quartely ICT status Report (previous quarter report) fro Management and Board | ICTM | √ |  |  |  | Quartly Report
[5 empty] | Perform Risk Assessment | kibiki , mohamed |  |  | √ |  | Risk Register
[5 empty] | Prepare/update ICT Inventory ,antivirus report | Hamza and Kibiki |  |  | √ |  | ICT Inventory Report
[5 empty] | Cunduct Monthly Department Meeting for every 1st week of next month | All | √ | √ | √ |  | Meeting minutes
|  |  |  | Cunduct ICT steering Committee meeting | Cunduct ICT steering Committee meeting every first month of the quarter |  | √ |  |  |  | Meeting minutes
|  |  | Cyber Security Awareness | To conduct Cyber Security awareness to 220 staff by June, 2023 | Conduct Cyber Security Awareness to all Staff | Mohamed |  |  | √ |  | training attendance
|  |  | To conduct 2 tests on Disaster Recovery site at NIDC and Iringa branch by June, 2023 | Conduct Disaster recovery test | Conduct disaster recovery test | Imary, mohamed, hamza |  |  | √ |  | Report
[5 empty] | Check backup test on NIDC and qnap storage | Imary, hamza |  |  | √ |  | test report
Note on J10: User: Will be on the beginning of second qtr , the first wk
Note on J19: User: Actual performanace will on the first week of previous wtr
Note on J23: User: This will overlap to another QTR

## Procurement Item
SN | Item | Type | Quantity | Budget | Status
1 | Data internet | TTCL Payment Monthly as per contract | 12 | 480000000
2 | PABX annual fee | Maintance fee as per contract paid quartely | 1 | 20000000
3 | Purchase of 48 Extension Phones (PABX) for Branches | new phones | 24 | 50400000
4 | Web, E-Mails, ERMS and eOffice annual fee | eGA payment annually as per contract | 1 | 50000000
5 | Purchase of Bulk sms | On demand |  | 50000000
6 | NIDC Services annual fee | Paid annually as per contract |  | 10000000
7 | Purchase of Inverter Systems 5KVA | Procurement | 23 | 276000000
8 | Mobile app hosting fee | annualy for IOS | 1 | 400000
9 | Call center annual fee | Annual payment |  | 20000000
10 | Sophos license fee | Annual payment |  | 30000000
11 | Antivirus fees | Annually |  | 20000000
12 | Patch Management System annual fee | Annually |  | 40000000
13 | Purchase of Network Switches | One time | 15 | 120000000
14 | Purchase of Network monitoring Tool (solarwind) | One time | 1 | 50000000
15 | Purchase of Fire Supression System | One time | 1 | 50000000
16 | Purchase of 65" Network Screen Monitoring (Smart TV) | One time | 1 | 5000000
17 | Workstation computers |  | 30 | 90000000
18 | Laptop Computers for Branch Managers |  | 27 | 162000000
19 | Purchase printers |  | 10 | 50000000
20 | Purchase projector |  | 27 | 54000000
21 | Purchase of Rollers |  | 18 | 6300000
22 | Purchase of Drums |  | 12 | 10800000
23 | Development Unit sets |  | 12 | 12000000
24 | Fuser Unit sets |  | 3 | 3600000
25 | Consultancy fee |  | 1 | 30000000
26 | To redesign Website, Mobile App & USSD by June, 2023 | Consultancy | 1 | 60000000
1750500000