## Annual Plan
Objective | Target | Main Activity | Sub Activity | Detailed Description | BI/NBI | Expected Output (milestone) | Means of verification | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Annual Budget 2022/23 | Responsible Person | Remarks
Operational capacity for service delivery enhanced | 95% of business processes automated | To review and improve the underwriting, claim, reinsurance, investment and reporting functionalities of IMIS system by June, 2023 | Conduct System Gap Analysis on General Insurance Underwriting | Perform end to end transaction with Users on General Individual , Corporate Undewriting and Undewrirting from external stakeholders banc assurance and intermediaries to identify defects | BI | Identified System Defects ,Complex UI that need to be simplified , Other user requirement | Gap Analysis report, user stories/requirement matrix, attendance ,minutes | [12 empty] | 108127500 | Imary, Daniel,Kasoma, mohamed, Frank,effort+User Department,Halima,editha | bar: Jul
|  |  |  | Review and approval requirement documents and user stories | NBI | Reviewed user requirement to improve the implemented system | Signed FRD , attendance and minutes, requirement matrix | [13 empty] | Imary, Daniel,Kasoma, mohamed, Frank,effort+User Department,Halima,editha | bar: Aug
|  |  | Design General Insurance undewriting process | Redesign the database Architecture | BI | Improved system design document for Individual underwriting | ERD diagram | [13 empty] | Imary, Daniel,Kasoma, mohamed, Frank,effort+User Department,Halima,editha | bar: Jul
|  |  |  | Develop data dictionery, data flows/activity diagram for Individual and Corporate undewriting process | BI | Improved system design document for Individual underwriting | Data Flows/activity diagram,Data Dictionery documents | [13 empty] | Imary, Daniel, mohamed, Frank,effort | bar: Aug to Sep
|  |  | Implement the system (coding) | Implement General Individual,Corporate underwriting based on the design document | BI | A system with structured database for easy reporting and consistent data | Weekly Progress report | [13 empty] | Imary, Daniel,Kasoma, mohamed, Frank | bar: Sep to Nov
|  |  |  | Implement General insurance Commision Payment process | BI | Improved General insurance Intermediary Commision Payment | Weekly Progress report | [13 empty] | Imary. Daniel, effort | bar: Dec
|  |  |  | Report development /improvement based on existing Systm and New System | BI | Improved reports interm of data and performance | Signed UAT/acceptance such as email/ change request agreement/helpdesk | [13 empty] | Editha, Halima, Frank | bar: Jul to Jun
|  |  | Conduct User Acceptance Test (UAT) | Cunduct UAT on general underwriting for individual and Corporate | BI | Ensure the developed system meet user needs | Signed UAT | bar: Dec
|  |  | Data Migration of General Insurance | Migrate Previous Data to New System, Verify Data Consistance and Accurancy | BI | All data from previous System migrated to new System | Migration Plan, Data Migration and verification Report | [13 empty] | ICT +GDI +Acturial and Risk | bar: Dec
|  |  | API Optimizations (external) | Redesgn and optimize Undewriting API, GePG , ERMSs and Notifications (SMS and Email ) ,TIRAMIS , banc assurance and smartPolicy cloud | BI | Improved API Interfaces that will be used for all integration to avoid inconsistent | API Document, UAT for smartPolicy cloud and on premises with Particular bank, skype conversation | [12 empty] | 103802400 | Imary, Daniel, Nyirenda, effort,machaba | bar: Jul to Sep; Dec
|  |  | Conduct System Gap Analysis of Life Underwriting Process | Perform end to end test with user on life undewriting (individual and Group) allocation , commision ,bonus and to identify issues/defects | BI | Identified System Defects ,Complex UI that need to be simplified , Other user requirement | Gap Analysis report, user stories/requirement matrix, attendance ,minutes | [12 empty] | 112452600 | Machaba, Sharifu , Kasoma,Mohamed, Nyirenda +User Departments,halima , editha | bar: Jul to Jun
|  |  |  | Review and approval requirement documents and user stories | NBI | Reviewed user requirement to improve the implemented system | Signed FRD , attendance and minutes, requirement matrix | bar: Aug
|  |  | Redesign the system to address the identified gap/issues | Redesign the database Architecture , Develop data dictionery, data flows for Individual and Group life undewriting process | BI | A system with structured database for easy reporting and data Accurancy and Consistency | Design Document , ERD and data flow diagram | [13 empty] | Machaba, Sharifu ,Mohamed , Nyirenda | bar: Jul to Jun
|  |  |  | Develop data dictionery, data flows/activity diagram for Individual and Corporate undewriting process | BI | Improved system design document for Individual underwriting | Data Flows/activity diagram,Data Dictionery documents | [13 empty] | Machaba, Sharifu ,Mohamed , Nyirenda | bar: Jul to Jun
|  |  | Implement the system (coding) | Implement Individual,Group life underwritings, Allocation , commision payment, Bonus based on the design | BI | Improved life, group insurance underwriting ,Allocations, Commision and bonus Payment | Signed UAT | [13 empty] | Machaba, Sharifu ,Mohamed , Nyirenda | bar: Jul to Jun
|  |  |  | Report development /improvement based on existing Systm and New System | BI | Improved reports interm of data and performance | Signed UAT/acceptance such as email/ change request agreement/helpdesk | [13 empty] | Halima, Editha,Frank | bar: Jul to Jun
|  |  |  | Migrate Previous Data from existing IMIS and all CIIS data to New System , Verify Data Consistance and Accurancy | BI | All data from previous design migrated to new design to improved reporting | Migration Plan and Data migration Verification report | [13 empty] | ICT +DLP +Acturial and Risk | bar: Jul to Jun
|  |  | Conduct User Acceptance Test (UAT) | Cunduct UAT on life underwriting for individual and Group and Comision | BI | Ensure the developed system meet user needs | Signed UAT | [13 empty] | user and ICT | bar: Dec
|  |  | Conduct System Gap Analysis and requirement elicitation general and life Insurance Claim process | Conduct System Gap Analysis and requirement elicitation general and life Insurance Claim process | BI | Identified System Defects ,Complex UI that need to be simplified , Other user requirement | Gap Analysis report, user stories/requirement matrix, attendance ,minutes | [13 empty] | machaba,imary,effort, sharifu,kasoma | bar: Jul to Jun
|  |  | Claim process Designing | Redesign General Claim process as per new underwiting architecture | BI | To improve claim procesing and reports | ERD ,data dictionery and data flow diagram/activity diagram | [12 empty] | 64876500 | Imary,Daniel,effort | bar: Jan
|  |  | Claim process Implementation(Coding) | Implementation (Claim process )(coding) | BI | Improved Claim management process | Weekly Progress report | [13 empty] | Machaba,Daniel,effort | bar: Jan to Feb
|  |  | Conduct User Acceptance Test (UAT) | Cunduct UAT on General and life claim process | BI | Ensure the developed system meet user needs | Signed UAT | [13 empty] | Machaba,Sharif,Nyirenda | bar: Jul to Jun
|  |  | Authentication Improvement | Implement two factor authentication (OTP) especially on Intermediary access | NBI | Improved accessibility of the systems | Signed UAT | [13 empty] | Daniel, Imary,Kasoma, Mohamed | bar: Feb
|  |  | CRM Improvement | Improve CRM and its integration to other module | NBI | Improved customer query handling and response | signed requirement, UAT | [13 empty] | Nyirenda, Kasoma,Mohamed | bar: Mar
|  |  | Investment module | Automation of money marketing and other remaining real estate requirement | BI | Automation of money marketing and other remaining real estate requirement | signed requirement and UAT | [12 empty] | 21625500 | Nyirenda,Sharif, Imary | bar: Jul to Jun
|  |  |  | Reissurance development as per new design | BI | Improved reisureance process | [13 empty] | 21625500 | Machaba, Effort, Sharif | bar: Jul to Jun
|  |  |  | Perform user training of IMIS System to Users | BI | To ensure that every one is conversant on using the system | Training report | [12 empty] | 30000000 | Halima, Editha,Frank,Kasoma+User Department | bar: Mar
|  | To perform preventive maintance on ICT devices quarterly by June, 2023 | Perform Preventive Maintanace | Perform Preventive Maintanance of computers and other ICT devices at HQ | BI | Improved performance, life ,efficiency , failure and unplanned downtime printers , | Report | [12 empty] | 138900000 | Hamza , Kibiki | bar: Jul; Dec
|  |  |  | Perform Preventive Maintanance for Printers |  | Improved performance, life ,efficiency , failure and unplanned downtime printers , | Preventive maitanance report | [13 empty] | Hamza , Kibiki | bar: Oct
|  |  |  | Perform Preventive Maintanance computers and other ICT branches as maintanance schedule | BI | Improved performance, life ,efficiency , failure and unplanned downtime printers , | Preventive Maitance Schedule and report | [13 empty] | Hamza , Kibiki | bar: Aug to Jun
|  |  |  | Perform preventive maintanance of UPS | BI | Improve efficient and performance | Report | [13 empty] | Hamza , Kibiki | bar: Oct
|  |  |  | Perform preventive maintanance at main data center | NBI | Improved performance, life ,efficiency , failure and unplanned downtime printers , | Report | [13 empty] | Hamza , Kibiki | bar: Dec
|  |  |  | Perform Preventive maintance of PABX phones | BI | Improved performance, life ,efficiency , failure and unplanned downtime | Job card | [13 empty] | Hamza , Kibiki | bar: Sep; Dec; Mar; Jun
|  | To facilitate management of Local Area Connection, Wide Area connection (WAN) and Wireless connection by June, 2023 | Network Monitoring and restructuring | Prepare Plan for Network restructuring | NBI | Improved guidance to restructure network without downtime | Network restructuring Plan | [12 empty] | 588150000 | Hamza , Kibiki | bar: Sep
|  |  |  | Restructure the network at HQ data ceter | BI | Improved network security and performance | Network restructuring Report | [13 empty] | Hamza , Kibiki | bar: Dec
|  |  |  | Configuration of LAN at Tanga and Arusha |  | Improved network security and performance | Configuration Report | bar: Oct
|  |  |  | Configuration of LAN at Katavi , Namanga, Zanzibar |  | Improved network security and performance | Configuration Report | bar: Sep
|  |  |  | Configuration of LAN at Dodoma |  | Improved network security and performance | Configuration Report | bar: Sep
|  |  |  | Upgrade Network devicess at branches per Plan | BI | Improved performance and security | Report | [13 empty] | Hamza , Kibiki | bar: Jan to Jun
Operational capacity for service delivery enhanced | 100 % of Compliance to regulations and Policies | Report Preparation | Report Preparation | Prepare Quartely ICT status Report for Management and Board, ICT steering Committee and eGA | NBI |  | Quartly Report | [13 empty] | ICTM
|  |  |  | Perform Risk Assessment | NBI | Reduce the likelihood of incidents to occur | Risk Register | [13 empty] | Kibiki, Mohamed,Halima
|  |  |  | Prepare/update ICT Inventory | NBI | Proper record of ICT equipment maintained | ICT Inventory Report | [13 empty] | Hamza , Kibiki | bar: Jul
|  |  |  | Cunduct Monthly Department Meeting for every 1st week of next month | NBI |  | Meeting minutes | [13 empty] | All | bar: Jul to Jun
|  |  | Cunduct ICT steering Committee meeting | Cunduct ICT steering Committee meeting every first month of the quarter | NBI | Improved ICT Governance | Meeting minutes | [13 empty] | ICTM, Mohamed | bar: Aug; Oct; Jan; Apr
|  | Prepare ICT Startegic Plan | Prepare ICT strategic Plan | Prepare ICT strategic Plan | BI | Direction toward ICT investment to support Corporate objective | ICT Strategic Plan | [12 empty] | 19350000 | ICTM | bar: Oct
|  | To conduct 2 tests on Disaster Recovery site at NIDC and Iringa branch by June, 2023 | Conduct Disaster recovery test | Conduct disaster recovery test | BI | Ensure recovery of data, restore business critical applications and continue operations after an incident | DR test report | [12 empty] | 36750000 | ICTM | bar: Dec; Jun
|  |  |  | Monitor daily backup and Perform backup test on NIDC and qnap storage | NBI | Ensure that data are available for recovery | Monthly Backup test report | [12 empty] | 0 | Imary,Kibiki | bar: Jul to Jun
|  | To assess security healthy level of the corporate and Penetration testing of the corporate systems by June, 2023 | Cunduct vulnearbility test and Penetration Test | Cunduct vulnearbility test and Penetration Test | BI | identified security weaknesses in the Corporation and Improvement | Pentration test report | [12 empty] | 40000000 | Mohamed | bar: Apr
|  | To facilitate system availability by June, 2023 | Review users and Use roles | Review user roles on all system (IMIS, ERMS, HRMIS, e-office | NBI | To ensure that only responsible individuals have specific roles on all systems | Signed User Roles | [13 empty] | Mohamed | bar: Sep; Dec; Mar; Jun
|  |  | Use rights to particular System | Train responsible Data owner on how to grant and remove user access on particular system | NBI | To allow user department to have full control on their system | Signed report | [13 empty] | Kasoma, Imary, Hamza, Halima | bar: Jan
|  |  | Facilitate Renewal of various services as per contract or license | Falitate procurement of renew of NIDC services | BI | improved sytem and service availability without outage | Contract Signed | [13 empty] | mohamed | bar: Sep
|  |  |  | Falitate procurement of renew of PABX services | BI | improved sytem and service availability without outage | Contract Signed | [13 empty] | Hamza , Kibiki | bar: Apr
Operational capacity for service delivery enhanced | 95 % of business processes automated | Develop sytem to manage Audit issues (internal & external) , TIRA, QMS (non conformity ), board matters arising | Develop Board and Management meeting management system | System to manage Board Meeting documents , management meeting and many other meeting | BI | Improve management and sharing of meeting documents | Concept Note, Design document and UAT | [12 empty] | 23100000 | Sharifu, Imary,Nyirenda | bar: Jul to Jun
|  | To enhance usability of e-Office system by June, 2023 | To enhance usability of e-Office system by June, 2023 | Integrate e-office system to other in-house system to ensure that document are stored on only on system | BI | Improved document management for the Corporation and digitaze all manual documents | Concept Note, Design document and UAT | [12 empty] | 32442500 | ICTM +Hamza,imary | bar: May
|  | To Improve Balanced scorecard (BSC) with Integration to core System (IMIS) | To Improve Balanced scorecard (BSC) with Integration to core System (IMIS) | BSC system reviewed and enhanced for better performance management within the Corporation | BI | Improved BSC system to access staff performance agaist Corporation performance | Concept Note, Design document and UAT | [12 empty] | 23997500 | Kasoma, Sharif +User Department | bar: Jul to Jun
|  | To improve Financial System June, 2023 | To enhace ERMS usability | To migrate ERMS system from Cloud to standalone for customization to meet Corporation requirement | BI | Improved performance and efficiency of the ERMS system | [13 empty] | 85795000 | Imary, Kibiki | bar: May
|  |  |  | Operationalize procurement and inventory/store process | BI | Improved effectiveness and efficiency of inventory and procurement | [14 empty] | Imary, Kasoma | bar: Nov
|  |  |  | Operationalize payroll process, planning and budgeting in ERMS system by June, 2023 | BI | Effectivenecy and efficient as currently no integration betweem HRMIS and ERMS | [14 empty] | Imary, kasoma | bar: Apr
|  | To conduct 2 tests on Disaster Recovery site at NIDC and Iringa branch by June, 2023 | Conduct Disaster recovery test | Conduct disaster recovery test | BI | Ensure recovery of data, restore business critical applications and continue operations after an incident | DR test report | [12 empty] | 36750000 | Mohamed | bar: Dec; Jun
|  |  |  | Monitor daily backup and Perform backup test on NIDC and qnap storage | NBI | Ensure that data are available for recovery | Monthly Backup test report | [12 empty] | 0 | Imary,Kibiki | bar: Jul to Jun
|  | To redesign Website, Mobile App & USSD by June, 2023 | To revamp Corporate website to be more interactive | To improve website to be more intractive and allow customer to buy our product themselves as well include live charts/chart bolts | BI | Improved selling channel and self service to customer that will improve customer expriences | Improved website . UAT | [12 empty] | 64470000 | Frank, effort | bar: Jan to Mar
|  |  | Improve mobile App | Mobile app improved by ading more fuctionality including claim notification and improve UX | BI | Improved visibility and customer expriene | report,UAT | [13 empty] | Frank, effort | bar: Mar to Apr
|  |  | Connect to social media particular whatsap | Allow user to underwrite to the Corporation through whatsap and apply AI on assiting Customer | BI | Improved customer experience and increase premium collection | report , UAT | [13 empty] | Frank, effort | bar: Apr to May
Human resources management and administration improved | % of staff trained | Conduct Training for all ICT Staff by June, 2023 | Attend training | To build capacity to ICT Staff on new technology and gap identified on performing daily activities | BI | [14 empty] | 60360000 | All ICT Staff | bar: Jul to Jun
|  | Cyber Security Awareness | To conduct Cyber Security awareness to all staff by June, 2023 | Conduct Cyber Security Awareness to all Staff | BI | Improved awareness to cyber security behaviuor | Attendance | [12 empty] | 116705000 | Mohamed,Editha,Halima | bar: Dec
Customer experience enhanced | 95% of customer satisfaction | Helpdesk Management,health check and Change Request | Resolve all helpdesk queries and change request | Resolve all helpdesk queries and change request | NBI | Improved customer satisfaction | Helpdesk response report | [13 empty] | All | bar: Jul to Jun
Operational capacity for service delivery enhanced | 100%ICT unit with risk register. | Implement Enterprise Risk management framework and Policy | To conduct risk register review by July 2022 | Ensure all emerging risks are identified indicators are determined , controls established and decision is sought for effective management | NBI | To ensure that all emerging risks are identified and mitigated. | Completed and signed off Departmental Risk Registers | [12 empty] | 0 | Kibiki | bar: Jul
|  |  | To collect and analyse actual Key Risk Indicator data on monthly and Quarterly basis |  | NBI | To establish trends in KRIs in order to determine the effectiveness of the existing controls | Key Risk Indicators Reports | [12 empty] | 0 | Kibiki | bar: Jul to Jun
|  |  | To prepare and submit monthly and quarter report on the collected and analyzed key risk indicators |  | NBI | To ensure that desion making process is risk-informed | Key Risk Indicators Reports | [12 empty] | 0 | Kibiki
|  |  | To implement and report status of developed mitigations to addres identified risks. |  | NBI | To ensure that the internal control environment is enhanced | Mitigation status implementation Reports | [12 empty] | 0 | Kibiki | bar: Jul to Jun
|  |  | To conduct monthly risk awareness sessions within the department. |  | NBI | To ensure that risk management is well incoporated in the organisational performance related activities | (i) Minutes and matters araising (ii) Attendance Sheet | [12 empty] | 0 | Kibiki
| Implement of Anti-Money Laundry and Anti-Fraud Program by June 2023 | Coordinate the implementation Quality Management System (QMS) | Collect and compile data for AML Reporting to FIU | Collect all indicators which might lead to mony laundring related to ICT and submit for effective management | NBI | Implement of Anti-Money Laundry and Anti-Fraud Program by June 2023 | AML Data Report | [12 empty] | 0 | Kibiki
|  |  | Preparation and submission of the Compiled Anti Money Laundry Data Report | [16 empty] | 0 | Kibiki
| Quality Management System (QMS) implemented by June, 2025 | Coordinate the implementation Quality Management System (QMS) | To develop and implement the corrective action plan to address non-conformities | Ensure plan and fucntions of the ICT Unit are effectively monitored, raise possible outliers to optimize service delivery | NBI | To ensure quality service delivery | Corrective Action Plan (CAP) | [12 empty] | 0 | Mohamed
|  |  | To perform functional objective performance analysis |  |  |  | Quarterly functional Objective Report | [12 empty] | 0 | Mohamed | bar: Jul to Jun
|  |  | To review and update the existing SOP |  |  |  | Signed and updated SOP | [12 empty] | 0 | Mohamed | bar: Aug